## Projects
ProjectID | ProjectName | Client | Department | ProjectManager | StartDate | PlannedEndDate | ActualEndDate | Status | Priority | Budget | ActualCost | PercentComplete
P001 | Website Redesign | Stark Logistics | Marketing | Zoe Brown | 2024-02-03 | 2024-04-27 |  | Not Started | Medium | 300000 | 0 | 0%
P002 | CRM Migration | Wonka Foods | Finance | Zoe Brown | 2025-03-28 | 2025-10-08 |  | In Progress | Medium | 60000 | 24527 | 39%
P003 | Mobile App Launch | Globex Corp | IT | Emma Garcia | 2025-04-04 | 2025-09-30 |  | In Progress | High | 40000 | 14259 | 35%
P004 | Marketing Campaign | Hooli Tech | HR | Aisha Costa | 2024-03-22 | 2024-11-09 |  | Delayed | Low | 150000 | 104804 | 60%
P005 | ERP Implementation | Stark Logistics | IT | Aisha Costa | 2025-03-16 | 2025-04-17 |  | Delayed | Medium | 250000 | 114774 | 36%
P006 | Data Warehouse Build | Acme Industries | HR | Emma Garcia | 2024-08-20 | 2024-09-19 |  | On Hold | Low | 80000 | 39103 | 45%
P007 | Cloud Migration | Wonka Foods | HR | Emma Garcia | 2024-06-01 | 2024-12-11 |  | In Progress | Medium | 100000 | 35488 | 34%
P008 | Product Rollout | Initech Solutions | HR | Emma Garcia | 2024-09-07 | 2024-10-11 | 2024-10-11 | Completed | High | 80000 | 75662 | 100%
P009 | Internal Portal Upgrade | Hooli Tech | HR | Diego Brown | 2024-09-05 | 2025-05-01 | 2025-05-08 | Completed | High | 40000 | 36054 | 100%
P010 | Customer Onboarding Automation | Initech Solutions | Product | Aisha Costa | 2025-03-22 | 2025-09-23 |  | In Progress | Medium | 250000 | 91376 | 35%
P011 | Payment Gateway Integration | Initech Solutions | IT | Aisha Costa | 2024-12-09 | 2025-06-23 |  | In Progress | High | 200000 | 157224 | 83%
P012 | HR System Upgrade | Northwind Retail | Finance | Emma Garcia | 2024-10-10 | 2025-01-06 |  | In Progress | Medium | 15000 | 3129 | 21%
P013 | Inventory Management Tool | Initech Solutions | Operations | Ken Patel | 2024-05-22 | 2024-12-09 |  | In Progress | High | 300000 | 181353 | 58%
P014 | Security Audit & Remediation | Northwind Retail | Product | Zoe Brown | 2024-02-19 | 2024-09-04 |  | In Progress | Low | 200000 | 107958 | 50%
P015 | Employee Training Platform | Initech Solutions | HR | Ken Patel | 2024-02-20 | 2024-04-05 |  | In Progress | High | 25000 | 10877 | 44%
P016 | Sales Dashboard Development | Wonka Foods | IT | Emma Garcia | 2024-04-03 | 2024-07-13 |  | In Progress | Medium | 25000 | 20790 | 81%
P017 | API Modernization | Hooli Tech | Operations | Diego Brown | 2024-10-03 | 2024-11-05 |  | On Hold | Low | 60000 | 27536 | 47%
P018 | Supply Chain Optimization | Hooli Tech | Finance | Ken Patel | 2025-04-07 | 2025-05-22 | 2025-05-12 | Completed | Medium | 150000 | 143412 | 100%
P019 | Brand Refresh | Initech Solutions | IT | Emma Khan | 2025-01-09 | 2025-08-27 |  | In Progress | Medium | 40000 | 27157 | 70%
P020 | Customer Support Chatbot | Wonka Foods | Marketing | Emma Garcia | 2024-02-01 | 2024-09-09 | 2024-08-30 | Completed | Low | 300000 | 312215 | 100%
P021 | Business Intelligence Rollout | Cyberdyne Systems | Marketing | Emma Khan | 2024-02-11 | 2024-04-28 | 2024-04-18 | Completed | Medium | 60000 | 60691 | 100%
P022 | Warehouse Automation | Umbrella Health | Marketing | Zoe Brown | 2024-11-13 | 2025-01-02 |  | In Progress | Medium | 250000 | 152027 | 61%
P023 | Vendor Portal Build | Globex Corp | IT | Ken Patel | 2024-05-02 | 2024-08-07 |  | In Progress | Medium | 80000 | 54935 | 67%
P024 | Compliance Tracking System | Stark Logistics | IT | Diego Brown | 2024-10-15 | 2024-12-09 | 2024-12-04 | Completed | Medium | 250000 | 239020 | 100%
P025 | Contract Management Tool | Wonka Foods | IT | Zoe Brown | 2024-03-21 | 2024-08-10 |  | Not Started | Low | 80000 | 0 | 0%
P026 | Social Media Analytics Tool | Globex Corp | Product | Emma Khan | 2024-06-02 | 2024-12-18 | 2024-12-13 | Completed | High | 80000 | 71694 | 100%
P027 | Legacy System Decommission | Umbrella Health | HR | Ken Patel | 2024-05-24 | 2024-11-24 | 2024-11-24 | Completed | High | 60000 | 67500 | 100%
P028 | Remote Work Enablement | Stark Logistics | Marketing | Zoe Brown | 2025-04-09 | 2025-05-22 | 2025-05-25 | Completed | Low | 80000 | 69411 | 100%
P029 | Loyalty Program Launch | Globex Corp | Product | Diego Brown | 2024-03-23 | 2024-10-28 |  | In Progress | Medium | 250000 | 160943 | 69%
P030 | Quality Management System | Stark Logistics | IT | Aisha Costa | 2025-03-03 | 2025-07-05 |  | In Progress | High | 40000 | 11685 | 30%

## Tasks
TaskID | ProjectID | TaskName | AssignedTo | StartDate | DueDate | Status | HoursEstimated | HoursActual
T0001 | P001 | Training Session | Omar Garcia | 2024-03-30 | 2024-04-17 | Not Started | 16 | 0
T0002 | P001 | Design Review | Liam Sharma | 2024-03-25 | 2024-04-24 | Not Started | 40 | 0
T0003 | P001 | Deployment | Anika Kim | 2024-02-14 | 2024-03-13 | Not Started | 40 | 0
T0004 | P001 | Data Migration | Sofia Nguyen | 2024-02-20 | 2024-03-01 | Not Started | 40 | 0
T0005 | P002 | QA Testing | Emma Sharma | 2025-05-17 | 2025-05-29 | Completed | 8 | 9
T0006 | P002 | Go-Live Support | Diego Brown | 2025-04-18 | 2025-05-01 | Completed | 24 | 23
T0007 | P002 | Documentation | Liam Sharma | 2025-04-22 | 2025-05-18 | Not Started | 24 | 0
T0008 | P002 | Deployment | Liam Patel | 2025-04-04 | 2025-04-17 | Completed | 60 | 76
T0009 | P002 | Stakeholder Sign-off | James Reddy | 2025-03-30 | 2025-04-07 | Not Started | 40 | 0
T0010 | P002 | UAT Session | Diego Brown | 2025-05-13 | 2025-06-12 | In Progress | 40 | 24
T0011 | P003 | UAT Session | Liam Sharma | 2025-04-20 | 2025-04-26 | Not Started | 40 | 0
T0012 | P003 | Vendor Coordination | Aisha Costa | 2025-05-07 | 2025-06-06 | Not Started | 80 | 0
T0013 | P003 | QA Testing | Ravi Costa | 2025-04-27 | 2025-05-15 | Completed | 80 | 100
T0014 | P004 | Training Session | Noah Muller | 2024-05-03 | 2024-05-21 | Blocked | 40 | 27
T0015 | P004 | Design Review | Emma Sharma | 2024-03-30 | 2024-04-10 | Not Started | 80 | 0
T0016 | P004 | Stakeholder Sign-off | Emma Sharma | 2024-05-04 | 2024-06-01 | In Progress | 60 | 35
T0017 | P004 | Data Migration | Carlos Brown | 2024-04-26 | 2024-05-01 | Blocked | 24 | 8
T0018 | P004 | Vendor Coordination | Aisha Costa | 2024-04-29 | 2024-05-24 | Blocked | 40 | 20
T0019 | P005 | Go-Live Support | Aisha Costa | 2025-05-07 | 2025-06-05 | In Progress | 80 | 33
T0020 | P005 | Development Sprint | Ravi Costa | 2025-03-25 | 2025-03-30 | Completed | 16 | 20
T0021 | P005 | Design Review | Carlos Brown | 2025-05-09 | 2025-06-07 | Completed | 40 | 40
T0022 | P005 | Stakeholder Sign-off | Emma Sharma | 2025-03-28 | 2025-04-24 | Not Started | 40 | 0
T0023 | P005 | Deployment | Anika Kim | 2025-03-31 | 2025-04-09 | Completed | 8 | 9
T0024 | P005 | Requirements Gathering | Noah Muller | 2025-03-27 | 2025-04-26 | Not Started | 8 | 0
T0025 | P006 | Design Review | Ken Patel | 2024-10-01 | 2024-10-22 | Not Started | 60 | 0
T0026 | P006 | Documentation | Diego Brown | 2024-10-19 | 2024-11-17 | On Hold | 60 | 46
T0027 | P006 | Development Sprint | Lucas Garcia | 2024-09-16 | 2024-10-08 | On Hold | 16 | 11
T0028 | P006 | Training Session | Diego Brown | 2024-09-17 | 2024-09-30 | Completed | 80 | 75
T0029 | P007 | Training Session | Noah Muller | 2024-06-19 | 2024-07-01 | In Progress | 24 | 10
T0030 | P007 | QA Testing | Aisha Silva | 2024-06-06 | 2024-06-15 | Completed | 16 | 15
T0031 | P007 | Stakeholder Sign-off | Noah Muller | 2024-07-16 | 2024-07-27 | Completed | 40 | 40
T0032 | P007 | Documentation | Emma Sharma | 2024-06-30 | 2024-07-18 | Completed | 16 | 19
T0033 | P007 | Design Review | Liam Sharma | 2024-07-28 | 2024-08-26 | Not Started | 80 | 0
T0034 | P007 | Deployment | Lucas Garcia | 2024-07-25 | 2024-08-23 | Not Started | 40 | 0
T0035 | P008 | Deployment | Ravi Costa | 2024-10-31 | 2024-11-18 | In Progress | 80 | 57
T0036 | P008 | Stakeholder Sign-off | Lucas Garcia | 2024-11-03 | 2024-11-15 | Completed | 16 | 14
T0037 | P008 | UAT Session | Emma Sharma | 2024-09-08 | 2024-09-25 | Completed | 80 | 91
T0038 | P009 | Documentation | Aisha Silva | 2024-09-06 | 2024-09-23 | Completed | 8 | 8
T0039 | P009 | Development Sprint | Ken Patel | 2024-10-30 | 2024-11-18 | Completed | 8 | 7
T0040 | P009 | Vendor Coordination | Emma Sharma | 2024-09-18 | 2024-10-07 | Completed | 24 | 28
T0041 | P009 | Data Migration | Lucas Garcia | 2024-09-22 | 2024-10-21 | Completed | 24 | 29
T0042 | P010 | Go-Live Support | Sofia Nguyen | 2025-05-21 | 2025-06-06 | Completed | 80 | 66
T0043 | P010 | Data Migration | Ravi Costa | 2025-05-09 | 2025-05-14 | Completed | 16 | 19
T0044 | P010 | Requirements Gathering | Carlos Brown | 2025-03-31 | 2025-04-12 | Completed | 40 | 45
T0045 | P011 | Documentation | Emma Garcia | 2025-01-16 | 2025-02-09 | Not Started | 80 | 0
T0046 | P011 | Stakeholder Sign-off | Lucas Khan | 2025-01-27 | 2025-02-06 | In Progress | 8 | 4
T0047 | P011 | Deployment | Aisha Costa | 2025-01-14 | 2025-02-09 | In Progress | 40 | 34
T0048 | P011 | Development Sprint | Anika Kim | 2024-12-13 | 2025-01-05 | Not Started | 80 | 0
T0049 | P012 | Go-Live Support | James Reddy | 2024-11-30 | 2024-12-08 | Not Started | 8 | 0
T0050 | P012 | Stakeholder Sign-off | Emma Khan | 2024-11-13 | 2024-12-01 | Not Started | 24 | 0
T0051 | P012 | Vendor Coordination | Lucas Garcia | 2024-11-11 | 2024-12-06 | In Progress | 8 | 6
T0052 | P013 | UAT Session | Liam Patel | 2024-07-06 | 2024-07-15 | In Progress | 16 | 11
T0053 | P013 | Deployment | Zoe Brown | 2024-06-30 | 2024-07-30 | Not Started | 40 | 0
T0054 | P013 | Documentation | Ken Patel | 2024-06-18 | 2024-07-16 | Not Started | 24 | 0
T0055 | P014 | Design Review | Emma Sharma | 2024-04-07 | 2024-04-26 | Not Started | 60 | 0
T0056 | P014 | Stakeholder Sign-off | Aisha Costa | 2024-03-11 | 2024-03-16 | In Progress | 24 | 7
T0057 | P014 | Documentation | Ravi Costa | 2024-03-12 | 2024-04-11 | In Progress | 24 | 9
T0058 | P014 | QA Testing | Diego Brown | 2024-04-03 | 2024-04-16 | Not Started | 8 | 0
T0059 | P015 | Design Review | Lucas Garcia | 2024-03-26 | 2024-04-24 | Completed | 80 | 83
T0060 | P015 | QA Testing | Emma Sharma | 2024-03-19 | 2024-04-18 | Completed | 8 | 7
T0061 | P015 | UAT Session | Lucas Garcia | 2024-04-04 | 2024-04-16 | In Progress | 80 | 48
T0062 | P015 | Documentation | Noah Muller | 2024-03-26 | 2024-04-16 | In Progress | 40 | 35
T0063 | P016 | Deployment | Ken Patel | 2024-04-17 | 2024-04-25 | Not Started | 16 | 0
T0064 | P016 | Documentation | Omar Garcia | 2024-04-10 | 2024-05-08 | Not Started | 80 | 0
T0065 | P016 | Stakeholder Sign-off | Liam Patel | 2024-04-15 | 2024-04-26 | Not Started | 40 | 0
T0066 | P016 | Vendor Coordination | Lucas Khan | 2024-05-19 | 2024-06-11 | Not Started | 60 | 0
T0067 | P016 | Data Migration | Lucas Khan | 2024-04-09 | 2024-04-20 | In Progress | 16 | 7
T0068 | P017 | Go-Live Support | Aisha Silva | 2024-10-20 | 2024-10-26 | Completed | 60 | 56
T0069 | P017 | Data Migration | Carlos Brown | 2024-11-12 | 2024-12-11 | On Hold | 8 | 6
T0070 | P017 | Development Sprint | Sofia Nguyen | 2024-10-21 | 2024-11-10 | On Hold | 40 | 17
T0071 | P018 | Documentation | Carlos Brown | 2025-04-11 | 2025-05-04 | Completed | 16 | 13
T0072 | P018 | Design Review | Carlos Reddy | 2025-06-06 | 2025-06-20 | Completed | 16 | 13
T0073 | P018 | Training Session | Zoe Brown | 2025-05-15 | 2025-06-08 | Completed | 60 | 59
T0074 | P018 | UAT Session | Sofia Nguyen | 2025-04-26 | 2025-05-19 | Completed | 24 | 26
T0075 | P018 | Go-Live Support | Liam Patel | 2025-05-16 | 2025-06-13 | Completed | 16 | 17
T0076 | P019 | Development Sprint | Ravi Costa | 2025-02-13 | 2025-02-20 | Completed | 8 | 8
T0077 | P019 | QA Testing | Lucas Khan | 2025-02-08 | 2025-02-22 | Completed | 16 | 15
T0078 | P019 | Go-Live Support | Liam Patel | 2025-02-22 | 2025-03-13 | Completed | 80 | 73
T0079 | P020 | UAT Session | Omar Garcia | 2024-03-13 | 2024-03-22 | Completed | 16 | 13
T0080 | P020 | Design Review | Lucas Khan | 2024-03-22 | 2024-04-05 | Completed | 40 | 34
T0081 | P020 | Data Migration | Zoe Brown | 2024-03-16 | 2024-04-02 | Completed | 60 | 64
T0082 | P020 | QA Testing | Ravi Costa | 2024-02-06 | 2024-03-01 | Completed | 40 | 46
T0083 | P021 | Requirements Gathering | Zoe Brown | 2024-03-18 | 2024-03-24 | Completed | 40 | 42
T0084 | P021 | Design Review | Lucas Garcia | 2024-04-09 | 2024-04-22 | Completed | 60 | 61
T0085 | P021 | QA Testing | Emma Garcia | 2024-02-16 | 2024-03-07 | Completed | 40 | 38
T0086 | P021 | Go-Live Support | Lucas Khan | 2024-04-05 | 2024-04-15 | Completed | 40 | 45
T0087 | P021 | Stakeholder Sign-off | Ken Patel | 2024-03-24 | 2024-04-10 | In Progress | 8 | 4
T0088 | P022 | Deployment | Diego Brown | 2024-12-25 | 2025-01-16 | In Progress | 40 | 9
T0089 | P022 | Design Review | Sofia Nguyen | 2024-12-06 | 2024-12-30 | In Progress | 80 | 40
T0090 | P022 | UAT Session | Lucas Khan | 2024-11-26 | 2024-12-09 | Not Started | 16 | 0
T0091 | P022 | Data Migration | Ravi Costa | 2024-12-11 | 2025-01-07 | In Progress | 8 | 1
T0092 | P022 | Requirements Gathering | Lucas Khan | 2025-01-03 | 2025-01-15 | Not Started | 16 | 0
T0093 | P023 | Data Migration | Aisha Silva | 2024-05-16 | 2024-05-24 | In Progress | 8 | 5
T0094 | P023 | UAT Session | Carlos Reddy | 2024-06-02 | 2024-06-29 | In Progress | 60 | 41
T0095 | P023 | Design Review | Aisha Silva | 2024-06-24 | 2024-07-14 | In Progress | 16 | 8
T0096 | P024 | QA Testing | Diego Brown | 2024-12-03 | 2025-01-02 | Completed | 24 | 30
T0097 | P024 | Vendor Coordination | Carlos Brown | 2024-11-01 | 2024-11-06 | Completed | 80 | 75
T0098 | P024 | Data Migration | Lucas Garcia | 2024-11-21 | 2024-12-17 | Completed | 16 | 16
T0099 | P024 | Development Sprint | Ken Patel | 2024-11-06 | 2024-11-21 | In Progress | 60 | 27
T0100 | P024 | Design Review | Carlos Reddy | 2024-12-09 | 2024-12-20 | Completed | 60 | 59
T0101 | P024 | Training Session | Emma Sharma | 2024-10-17 | 2024-11-01 | Completed | 80 | 100
T0102 | P025 | Training Session | Zoe Brown | 2024-04-22 | 2024-05-15 | Not Started | 8 | 0
T0103 | P025 | Go-Live Support | Aisha Silva | 2024-03-27 | 2024-04-17 | Not Started | 8 | 0
T0104 | P025 | Development Sprint | Lucas Garcia | 2024-04-16 | 2024-05-11 | Not Started | 8 | 0
T0105 | P025 | Documentation | Emma Sharma | 2024-05-10 | 2024-05-23 | Not Started | 60 | 0
T0106 | P025 | Requirements Gathering | Noah Muller | 2024-05-01 | 2024-05-08 | Not Started | 80 | 0
T0107 | P025 | Design Review | Sofia Nguyen | 2024-04-14 | 2024-04-29 | Not Started | 60 | 0
T0108 | P026 | QA Testing | Emma Garcia | 2024-06-16 | 2024-07-14 | Completed | 40 | 51
T0109 | P026 | Training Session | Sofia Nguyen | 2024-06-30 | 2024-07-10 | Completed | 8 | 6
T0110 | P026 | Stakeholder Sign-off | Diego Brown | 2024-06-20 | 2024-07-06 | Completed | 40 | 34
T0111 | P027 | Vendor Coordination | Aisha Silva | 2024-07-02 | 2024-07-19 | Completed | 40 | 50
T0112 | P027 | Training Session | Liam Sharma | 2024-06-07 | 2024-06-26 | Completed | 40 | 37
T0113 | P027 | Development Sprint | Omar Garcia | 2024-07-20 | 2024-08-19 | Completed | 24 | 27
T0114 | P027 | Go-Live Support | Carlos Reddy | 2024-05-28 | 2024-06-16 | Completed | 60 | 56
T0115 | P027 | Data Migration | Emma Sharma | 2024-07-07 | 2024-07-20 | Completed | 24 | 21
T0116 | P027 | Requirements Gathering | James Reddy | 2024-07-17 | 2024-08-06 | Completed | 16 | 15
T0117 | P028 | Go-Live Support | Lucas Khan | 2025-04-09 | 2025-05-02 | Completed | 60 | 70
T0118 | P028 | Stakeholder Sign-off | Anika Kim | 2025-05-28 | 2025-06-27 | Completed | 60 | 72
T0119 | P028 | Requirements Gathering | Aisha Silva | 2025-05-19 | 2025-05-30 | Completed | 80 | 94
T0120 | P028 | UAT Session | Sofia Nguyen | 2025-05-19 | 2025-05-27 | Completed | 24 | 28
T0121 | P028 | Training Session | Ken Patel | 2025-05-16 | 2025-06-01 | Completed | 8 | 10
T0122 | P029 | Development Sprint | Lucas Garcia | 2024-04-24 | 2024-05-07 | Completed | 24 | 30
T0123 | P029 | QA Testing | Emma Garcia | 2024-05-13 | 2024-05-27 | Not Started | 24 | 0
T0124 | P029 | Go-Live Support | Emma Sharma | 2024-04-21 | 2024-04-28 | Completed | 16 | 19
T0125 | P029 | Data Migration | Emma Khan | 2024-05-16 | 2024-06-15 | Not Started | 24 | 0
T0126 | P029 | Deployment | Zoe Brown | 2024-05-12 | 2024-05-29 | Completed | 24 | 25
T0127 | P029 | Stakeholder Sign-off | Liam Patel | 2024-04-15 | 2024-05-11 | Not Started | 80 | 0
T0128 | P030 | Training Session | Emma Khan | 2025-04-11 | 2025-05-03 | In Progress | 60 | 21
T0129 | P030 | Deployment | Carlos Reddy | 2025-04-12 | 2025-05-01 | Not Started | 24 | 0
T0130 | P030 | Design Review | Lucas Garcia | 2025-03-10 | 2025-03-19 | Completed | 8 | 7
T0131 | P030 | QA Testing | Zoe Brown | 2025-03-10 | 2025-03-18 | Completed | 60 | 52
T0132 | P030 | Documentation | Noah Muller | 2025-03-26 | 2025-04-21 | Not Started | 80 | 0
T0133 | P030 | Requirements Gathering | Aisha Silva | 2025-03-29 | 2025-04-21 | Not Started | 80 | 0

## Employees
EmployeeID | EmployeeName | Role | Department | HourlyRate
E001 | Liam Sharma | UX Designer | Marketing | 50
E002 | Sofia Nguyen | Business Analyst | Product | 75
E003 | Emma Khan | Scrum Master | IT | 35
E004 | Emma Garcia | QA Engineer | HR | 80
E005 | Aisha Silva | QA Engineer | Product | 75
E006 | Omar Garcia | DevOps Engineer | HR | 55
E007 | Aisha Costa | Developer | Product | 65
E008 | Anika Kim | Developer | Marketing | 60
E009 | Liam Patel | Scrum Master | IT | 60
E010 | Lucas Khan | UX Designer | IT | 70
E011 | Ken Patel | Scrum Master | IT | 75
E012 | James Reddy | Data Analyst | HR | 50
E013 | Emma Sharma | QA Engineer | Finance | 40
E014 | Carlos Reddy | Business Analyst | Operations | 55
E015 | Zoe Brown | Data Analyst | Marketing | 60
E016 | Lucas Garcia | UX Designer | Product | 40
E017 | Diego Brown | Developer | HR | 50
E018 | Noah Muller | Scrum Master | Finance | 75
E019 | Carlos Brown | Data Analyst | IT | 50
E020 | Ravi Costa | Data Analyst | Operations | 55